## Gannt Chart
PROJECT: Threat Systems Pty Ltd - Cyber Solution
| Threat Systems Pty Ltd - Cyber Solution |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Hayden Cook
| Project start date: | 2024-07-17 |  |  |  |  | July | [13 empty] | August | [27 empty] | September
| Scrolling increment: | 5 | time axis 2024-07-22 to 2024-10-05
| Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2024-07-22 to 2024-10-05
Project Implementation
0 | Kick Off Meeting | On Track | All | 100% | 2024-07-29 | 1
0 | Creating and setting up Splunk | Med Risk |  | 0% | 2024-08-22 | 7
1 | Virtual Machine Setup | Med Risk |  | 0% | 2024-08-29 | 7
2 | Vulnerability scan | Low Risk |  | 0% | 2024-09-05 | 7
3 | Scan report | Low Risk |  | 0% | 2024-09-12 | 7
4 | Proof of concept demo | Low Risk |  | 0% | 2024-09-19 | 7
1 | Implementation plan for deployment | High Risk |  | 0% | 2024-08-22 | 7
6 | Documentation | Low Risk |  | 0% | 2024-10-03 | 7
5 | Training | Low Risk |  | 0% | 2024-09-26 | 7
6 | Final report | Low Risk |  | 0% | 2024-10-03 | 7

## Sheet1
TASK NO | TASK NAME | DURATION | RESOURCE | PREDECESSORS
1 | Creating and setting up Splunk | 1 week |  | 0
2 | VM Setup | 1 week |  | 1
3 | Vulnerability scan | 1 week |  | 2
4 | Scan report | 1 week |  | 3
5 | Proof of concept demo | 1 week |  | 4
6 | Implementation plan for deployment | 1 week |  | 1/0
7 | Documentation | 1 week |  | 6
8 | Training | 1 week |  | 5
9 | Final report | 1 week |  | 6
10 | Insert more as required….